## GPPB BAF
GP Provider Board - Board Assurance Framework
Version: | 1
Date of last revision: | 2023-07-13
Last revision manager: | Ian Creek
Strategic priority | Risk / Gaps | Date added | Current risk score | Initial risk score | Lead | Actions | Progress update | Date of last update
Workforce | Significant no. of practices short staffed | 2023-02-15 | 20
Workforce | Significant no. of PCNs under-recruited | 2023-02-15 | 8
Workforce | Workforce programmes are at risk with current system redesign - e.g. Pharmacy (via Helen Stapleton), no PC Worforce Implimentation Group | 2023-02-15 | 12
Workforce | No lead for workforce identified on GPPB | 2023-02-15 | 12
Quality and safety | Significant no. of practice reporting Opel 3/4 reguarly | 2023-02-15 | 20
Quality and safety | Lack of integrated approach to practice resilience | 2023-02-15 | 16
Quality and safety | Not enough resource available to turn practices around | 2023-02-15 | 16
Quality and safety | Lack of clear data to identify practices at risk | 2023-02-15 | 16
Quality and safety | Community Pharmacy increasingly at risk (regular closures) | 2023-02-15 | 16
Quality and safety | Pathways and clinical information not easy to access for GP teams | 2023-07-13 | 16 |  | Ian Creek | TeamNet CSI launched | First services launched 07/23 | 2023-07-13
Service delivery | EA at risk in current environment - stretches practices too far | 2023-02-15 | 16
Service delivery | Integrated services not commissioned or at risk - e.g. dermatology, menopause and vasectomy | 2023-02-15 | 16
Service delivery | Lack of alinment of providers to work at scale | 2023-02-15 | 12
Service delivery | GPPB not fully aware of all service development in PCNs | 2023-02-15 | 9
Service delivery | No GPPB plan for service development | 2023-02-15 | 9
GPPB Development | Not yet 100% represented in all system meetings | 2023-02-15 | 15
GPPB Development | No PMO commissioned and funded to support GPPB - SPH roles not clarfied and agreed | 2023-02-15 | 15
GPPB Development | No areas of responsibility identified for GPPB members | 2023-02-15 | 15
GPPB Development | Fragmented communication | 2023-02-15 | 8
GPPB Development | No data and reporting | 2023-02-15 | 20
GPPB Development | No GPPB strategy published | 2023-02-15 | 15
GPPB Development

## Risk scoring guide
Identified risks will be rated using the below.

## Risk Archive
Removed or mitigated risks will be archived here

## Development agenda 2022-23
Areas of focus as collated post December GPPB development sessions
· Developing a network/community of practice/or other forum(s) to create a shared sense of a GP family across Somerset. (PMO Function – SPH)
· Developing a suite of support measures or means of describing support that can realistically be offered or a mechanism to access this (Provider group)
· Working with data analysts/existing business intelligence provisions to develop access to required data– task and finish group to progress this (SPH and Task/Finish Group)
· Stakeholder mapping exercise – to approach engaging and networking with a range of system partners – linked to building case for management/operational leadership and clinical leadership capacity within the GPPB. (? Not sure what this is)
· Develop provider collaborative. (SPH)
· Develop business case around existing project to take to ICS (Provider Group)
· Develop business case proposal for management role within GPPB to take to ICS (SPH) Need to check what this means though?
· Develop project management function (SPH) and a programme of projects also needed
· Develop a five-year plan for GPPB (added by IC)
Immediate (6 months):
o New GPPB agenda approach
o EA
o Step 2 beds
o Other Winter projects – e.g. pharmacy closures – warm spaces???
o Reporting and business intelligence development – invite OneCare to GPPB in January. This will need dedicated resource (SPH can offer time through IC and JL now, but will need more once a spec is developed)
o Provider group formation:
§ Provider offers summary
o Collect best practice an new ideas to back/support – will need prioritisation
o Practice resilience – stronger and more integrated approach
o Develop GPPB comms plan and allocate resource to this ongoing
o Develop business case for PMO resource and how it will interface with system (recommend it reports to GPPB).
Short (6 months to 2yrs)
o GP flexible pool growth and diversification
o Diabetes and Lipids – one essential high risk area
o 2 new Integrated services – e.g. Dermatology and Menopause service
o Develop an estate plan on PCN footprints
o Create a regular Clinical Council and online community of practice
o What could we do that is better than the PCN DES?
Medium term (2 – 5yrs)
o Pharmacy hubs
o Admin hubs
o New estates plan started
o Further integrated services